Mohamed bin Zayed Species Conservation Fund
Schedule and financial report
Schedule

Time of field survey
21 days, 18 September ‑ 8 October 2016.

Field work locations
Son La province, Moc Chau district (Xuan Nha, Chieng Son, Tan Xuan, Long Sap communes), Yen Chau district (Long Phieng, Phieng Khoai communes).
Team (6 persons)
Project leader: Leonid V. Averyanov.
Participants: Nguyen Tien Hiep, Nguyen Sinh Khang, Chuong Quang Ngan.

Volunteers: Tatiana Maisak, Nguyen Truong Son.
Trasportation
2 cars, 2 drivers: Vu Xuan Manh, Nguyen Quang Hieu.

Field work schedule

	Day №
	Date
	Location
	Activity description

	1
	18.09.16
	L.Averyanov, T.Maisak
	Arrive to Hanoi

	2
	19.09.16
	L.Averyanov, T.Maisak, Hiep, Khang, Ngan, Two driver (Manh, Hieu)
	Project team leave Hanoi for Son La Province; prepare logistic for field, stay in Son La City

	3
	20.09.16
	Son La prov.
	Processing of permissions for work in Son La.

	4
	21.09.16
	Son La prov., Moc Chau district, Chieng Son commune.
	Staff move to Moc Chau district; permission paper work; staff move to Xuan Nha nature reserve, Chieng Son commune.

	5
	22.09.16
	Son La prov., Moc Chau district, Chieng Son
	Field survey in Chieng Son commune area

	6
	23.09.16
	Son La prov., Moc Chau district, Chieng Son
	Field survey in Chieng Son commune area

	7
	24.09.16
	Son La prov., Moc Chau district, Xuan Nha commune
	Field survey in Xuan Nha commune area

	8
	25.09.16
	Son La prov., Moc Chau district, Xuan Nha commune
	Field survey in Xuan Nha commune area

	9
	26.09.16
	Son La prov., Moc Chau district, Long Sap commune
	Field survey in Long Sap commune area

	10
	27.09.16
	Son La prov., Moc Chau district, Long Sap commune
	Field survey in Long Sap commune area

	11
	28.09.16
	Son La prov., Moc Chau district, Tan Xuan commune
	Field survey in Tan Xuan commune area

	12
	29.09.16
	Son La prov., Moc Chau district, Tan Xuan commune
	Field survey in Tan Xuan commune area

	13
	30.09.16
	Son La prov., Yen Chau district, Long Phieng commune
	Staff move to Yen Chau distict 

	14
	01.10.16
	Son La prov., Yen Chau district, Long Phieng commune
	Field survey in Long Phieng commune area

	15
	02.10.16
	Son La prov., Yen Chau district, Long Phieng commune
	Field survey in Long Phieng commune area

	16
	03.10.16
	Son La prov., Yen Chau district, Phieng Khoai commune
	Field survey in Phieng Khoai commune area

	17
	04.10.16
	Son La prov., Yen Chau district, Phieng Khoai commune
	Field survey in Phieng Khoai  commune area

	18
	05.10.16
	Son La prov., Yen Chau district, Yen Son commune
	Field survey in Yen Son  commune area

	19
	06.10.16
	Son La prov., Yen Chau district, Yen Son commune
	Field survey in Yen Son commune area

	20
	07.10.16
	Hanoi
	Field staff leave Yen Chau for Hanoi

	21
	08.10.16
	Hanoi
	Processing of collections 

	22
	09.10.16
	Hanoi
	L.Averyanov, T.Maisak leave Hanoi


Brief financial report
Project budget USD 12000

2 cars rent during 21 days field work for 4525 km (for cost USD 0.38 per km), 4525 x 0.38 x 2 = USD 3440
Gasoline and oil for 2 cars for 4525 km - USD 1400
Road payments USD 220
Hiring motorbikes/driver for staff and field equipment transportation in mountain trails USD 700
Living cost of the project leader - Prof. L.Averyanov and project participant - T.Maisak in Hanoi 3 nights including Hotel and meal USD 180
Voucher herbarium specimens processing and shipment, about 2000 specimens – USD 600
Field expenses: organizing, permissions processing, phyto-certificate processing for collections export, primary collection processing, payment for National Reserve, hiring of local guides, porters and assistants, field supplies – USD 1150
Meal for 8 persons (6 project participants and 2 drivers) during 18 days (1 person, USD 22 per day, 8 x 18 x 22) – USD 3168
Accomodation for 8 persons (6 project participants and 2 drivers) during 18 days (1 person, USD 5 per day, 8 x 18 x 5) – USD 720
Post, Fax, Telephone and miscellations – USD 200
Laboratory analysis, material processing, herbarium label writing an printing, sorting od herbarium specimens – USD 250
Total from Mohamed bin Zayed SCF: USD 12028
Salary of the Project participants for period of field and laboratory works – about USD 10000
Round air tickets of 2 foreign Project participants and baggage transportation – USD 1400
Processing, treatment, sorting, mounting, housing voucher herbarium specimens – USD 600

Fieldwork equipment, including photo cameras, laptops, extra batteries , herbarium paper etc. – USD 800

Total from other sources: USD 12800

Total Project cost: USD 24828
