Project number: 152511623

Target species: Acacia belairioides

MAIN RESULTS

(Second Report)

Activities

I. Field work

This activity has already concluded and this moment two scientific publications are prepared: one on the size and structure of the population and main threats of Acacia belairioides and the second about optimal microsites for the germination and establishment of the seedlings in the activity of restoration or reinforcement of natural populations. These publications also show the conservation status of A. belairioides according to IUCN criteria.

II. Establishment of a nursery for de propagation of species

There are 373 seedlings (survivor nursery activity) for the reinforcement of the natural population and delivery of some plants for botanic gardens, schools and parks of the city. In addition, a protocol (technical instruction) for the reproduction of the species in nursery is being made. This propagation protocol contains basic information for obtaining seeds and seedlings (e.g., period of collection of fruits and seeds, pregermination treatments to eliminate dormancy and adequate light conditions for the growth of the seedlings).

III. Reinforced of the natural populations

This activity has not begun. The reinforcement activity will only be carried out in the locality of San Andrés, where we only find seven adult individuals. There are already more than 300 seedlings in nursery for the activity of reinforcement, but we must wait until May when the rains begin, because otherwise the reinforcement would not be successful. The seedlings already have a height at 20 cm and more than three branches.

IV. Training technical staff of protected areas and other environmental activities.

- Printing of 200 informative materials on Acacia belairioides and delivery to people from communities close to the habitat of the species, personal technician of the protected area and primary and secondary schools of city of Holguín.

- Print two Posters with project results for informative talks and scientific events.